## Merchant web
|  |  | Project Name | Merchant web | Siinqee Bank Digital Directorate
Project Manager
Tested by
Delivered date
Start date
End date
Test ID | Features | Test Cases | Expected Result | Actual Result | PASS / FAIL | Remarks | Developer Comments
TC-01 | Login | 1, login | by using phone number & pin login successfully |  | PASS
|  | 2. forceful pasword change | Password force change on first login |  | Not available for test | it doesn't force to change password but redirect to password change dashboard
|  | 3. Invalid login pin count and block | counts wrong login attempts and blocks user |  | PASS |  | Accepted
TC-02 | Profile | 1, update profile | profile is updated |  | PASS | works except date of birth | Accepted
TC-03 | Logout | 1, logout | logout from the system
TC-04 | Sign up | 1, create my account | by using phone number & verification code login to the system successfully |  | PASS
TC-05 | setting | 1, change password | change old password result is done |  | PASS | must redirect to login page after pin is changed
TC-06 | Dashboard | 1, report title | display report title |  | we don't have test data | unable to make transaction
|  | 2, fliter by year | search result displayed by year |  | we don't have test data | unable to make transaction because of that there will be no data for test
|  | 3, fliter by month | search result displayed by month |  | we don't have test data | unable to make transaction because of that there will be no data for test
|  | 4. filter by week | search result diplayed by week |  | Not available for test | unable to make transaction because of that there will be no data for test | rejected: we don't filter by week, we can use date range instead of it. On week graph we display current week incomes
|  | 4, fliter by specific date | search result displayed by specific date |  | we don't have test data | unable to make transaction because of that there will be no data for test
|  | 5, fliter by date range | search result displayed by date range |  | we don't have test data | unable to make transaction because of that there will be no data for test
|  | 6, fliter by selected sales agent | search result displayed by sales agent |  | we don't have test data | unable to make transaction because of that there will be no data for test
|  | 7, clear fliter | displayed search data change in to default data |  | we don't have test data | unable to make transaction because of that there will be no data for test
|  | 8, apply fliter | use "search" option as usual |  | we don't have test data | unable to make transaction because of that there will be no data for test
|  | 9, total income card's | displayed total income card's by Ethiopian's birr |  | we don't have test data | unable to make transaction because of that there will be no data for test
|  | 12, active sales agents | display pending actives sales agents resutls based on provided different dates |  | PASS
|  | 13, performance report graph | performance report graph displayed by selected year. |  | we don't have test data
|  | 14, Sales Overview report graph | Sales Overview report graph displayed by selected year, months |  | we don't have test data
|  | 15. Report dowenloading | Dashboard report will be dowenloaded |  | Not available for test
|  | 16. Merchant made any changes needs approval (Maker checker concept) |  |  | Not available for test | ths system doesn't have the functionality
17
TC-07 | Sales agent Management | 1, sales agent requeste(sales agent request tab) | Active |  | PASS | shows approved by column but doesn’t show previously approved or rejected reqeusts Doesn’t show reqeust type
|  | 2, columns | add columns and displayed successfully |  | PASS
|  | 3, add sales agent | sales agents are added to correctly |  | PASS
|  | 4, search by name | search result are displayed bay name |  | PASS | Works but not as expected
|  | 5, update,activate and cancel | all status result displayed |  | PASS
|  | 6, search by status | all status result displayed |  | PASS | the status for locked (suspended) user is not defined
|  | 7;search by phone | search result by phone starting by ( 251../09../07../2517...) should be displayed |  | PASS
|  | 8.search by name and status | It must include the search |  | PASS
|  | 9 Deativate Sales Agent info | Sales agent deactivatd and status should set deactivated |  | PASS | Alters the work status to outoffice authomaticaly The terminology differs the system uses suspended as status for diactivation
|  | 10. Reset sale agent account and agent PIN | sale agent account and sales agent PIN reseted |  | PASS |  | Accepted
|  | 11, columns | add and disable columns and displayed successfully
|  | 12, Download Sales Agnet list Report | Dowenload Sales agent list |  | Not available for test | feature update
|  | 13. Activate a deactivated Customer | re-activates a deactivated customer |  | PASS
TC-08 | Transaction history | 1, search by agent name | search result by agent name has been displayed |  | PASS
|  | 2, search by date rage | search result by date range displayed correctly |  | Not available for test | unable to make transaction because of that there will be no data for test
|  | 3, columns | add and disable columns and displayed successfully |  | PASS
|  | 4, Transaction history report viewing and downloding with a date range | dowenloads transaction history with in a given range |  | Not available for test | feature update
TC-09 | Bill Management | 1, add bills | bill added successfully |  | PASS
|  | 2, prepared bill payment by QR | prepared bill payment by QR pending status |  | PASS
|  | 3, bill paid status | bill paid status result change in to paid |  | Not available for test | unable to make transaction because of that there will be no data for test
|  | 4, add bill and enter amount | enter amount with cen examples 2.5 amount added correctly |  | PASS
|  | 5, add bill with zero amount | add bill with zero amount display erorr with empty amount |  | PASS
|  | 6, update bill | update amount, currency and description are displayed |  | PASS
|  | 7,transfer bill | sales agents are updated to correctly |  | PASS | merchant can transfer bill to the owner twice
|  | 8, search by name | search results by names are displayed |  | PASS
|  | 9, status | search result by status displayed |  | PASS | There is no transferd status bills filter
|  | 10, number of showing data | the result of number of showing data number and displayed data numbers are equal |  | PASS |  | Accepted
|  | 11, transfer pending bills | update bills are displayed |  | PASS | Dosent show specific type of request (wheter the request is transfer or canclation reqeust)
|  | 12, create static bill to be used multiple times |  |  |  | IPS supports both static and dynamic pymnet types | New fueture: Will be considered in future release
|  | 13, dowenload all bill report based on date range |  |  | Not available for test | feature update
|  | 14. search by branch |  |  | PASS | filter works but storing a 0 value for all the bills created on agent app | Accepted
TC-10 | Transaction update | 1, Transaction update |  |  | Not available for test |  | Accepted
TC-11 | Branche Management | 1, add branches | branches are added |  | PASS | Customers may choose to identify their location using the map or different options, making latitude and longitude numbers less preferable there must be a maker chaker concept on this cenarieo
|  | 2, search by branches name | search result by branches are displayed |  | PASS
|  | 3, Merge Branchs | Merge 2 branchs to 1 |  | PASS | Data must persist on previously Split must be optional if some one made a mistake of merging two branchs
|  | 4, update branches | branches are updated as expected |  | PASS | there must be a maker chaker concept on this cenarieo
5,
6,
7,
TC-12 | Setting | 1,In Limit Amount,Limit Pending Bill,Access To Generate Qr,Bill Aloud and Distance range : add new default setting | default setting added |  | PASS |  | Accepted
|  | 2,In Limit Amount,Limit Pending Bill,Access To Generate Qr,Bill Aloud and Distance range : add new Specific setting | specific setting added |  | PASS |  | Accepted
|  | 3,In Limit Amount,Limit Pending Bill,Access To Generate Qr,Bill Aloud and Distance range: update default setting | update result displayed |  | PASS |  | Accepted
|  | 5, enable default setting | Successfully Enabled Message Displayed |  | PASS
|  | 6,disable default setting | Successfully disabled Message Displayed |  | PASS
|  | 7.try update default setting & leave by no | No message should be displayed |  | PASS
TC-13 | Word correction | 1,All Word typos | regular words |  | PASS

## Merchant App
|  |  | Project Name | Merchant App
Project Manager
Tested by
Start date
End date
Test ID | Features | Test Cases | Expected Result | Actual Result | PASS / FAIL | Remarks | Developer Comments
TC-01 | Authentication | 1, Login with valid credentials, | Successfully logged in and redirected to the merchant dashboard. No error messages displayed. |  | PASS | after forceful password change the ,the App should redirect the merchant to login page so that he can login with the new changed password
|  | 2, Logout from merchant account. | User is logged out and redirected to the login page. |  | PASS
TC-02 | Agent Management | 1, Add a new sales agent | New agent is added to the agent list with status "New" . Confirmation message displayed. |  | PASS
|  | 2, View Sales Agent Info | Sales Agent information page is displayed Or Agent Details Displayed |  | PASS
|  | 3, Activate New Sales Agent | User Activated Success Message Displayed And Pin and Also Activation Code Sent |  | PASS
|  |  | User Deactivated Successfully |  | PASS | if the Deactivation is done while the Agent is in loggin session ,he can continue using the app, can generate bill as long as he's not loggedout
|  | 4, Deactivate Sales Agent | User reactivated Successfully |  | PASS |  | Accepted
|  | 5, Reset User | User Reset Successfully Message displayed And New Activation Code Sent |  | PASS
|  | 6, Reset Pin | Pin Reset Successfully Message Displayed And New Pin Will be Send |  | PASS
|  | 7, Cancel User | User Canceled successfully |  | PASS
|  | 8, Search Sales Agent by name | The Sales Agent details Displayed |  | PASS
|  | 9, Search Sales Agent by phone | The Sales Agent details Displayed |  | PASS
|  | 10, Agent Requests | Approving Pending Agent Requests(cancel and transfer) |  | PASS
|  | 11,Agent Activation | The Agent Activated Successfully by Logged in In The Agent App |  | PASS
TC-03 | Report | 1, View daily, monthly and yearly income reports from the merchant dashboard (Home). | Reports (Total Transactions, Total revenue, Active Agents) are displayed |  | we don't have test data
|  | 2, Filter Income Reports in month | Income reports (Total Transactions, Total revenue, Active Agents) are displayed, using the selected month |  | we don't have test data
|  | 3, Filter Income Reports in date | Income reports (Total Transactions, Total revenue, Active Agents) are displayed, using the selected date |  | we don't have test data
|  | 4, Filter Income Reports Using Agent Name | Income reports (Total Transactions, Total revenue, Active Agents) are displayed, using the selected agent. |  | we don't have test data
|  | 5, Filter Income Reports By Date Range.(In Home Tab) | Income reports (Total Transactions, Total revenue, Active Agents) are displayed, using the selected period and agent. |  | we don't have test data
|  | 6, Filter Income Reports Using By Date, Daily , Weekly(in History Tab) | Transactions That done by The Agent Is Diplayed |  | we don't have test data
TC-04 | Configuration | 1, Verify bills listed. | Bills listed properly with appropriate information. |  | PASS
|  | 2, Add New Bill to Bill list(Create Bill Tab) | New Bill Is Added To The List With Specific agent That Selected |  | PASS
|  | 4, Scanning QR CODE | Qr Code Details Displayed In The Scanning Tools(Receiver account,Receiver Name,Amount,Tip..) |  | Not Available for test
|  | 5, Filter bills by Agent name in Agent list drop down | Only bills associated with the entered Agent Name are displayed if no matching Agent Name is found, a "No results found" message should be displayed. |  | PASS
|  | 6, Filter bills by Status (Create Bill tab) | Only bills with the selected status are displayed in the "Bills List" table |  | PASS
|  | 7, Filter bills by Date (Create Bill tab) | Only bills with the selected Date are displayed in the "Bills List" table |  | PASS
|  | 8, Edit Bill | The "Bill Info" page is displayed, showing the bill details |  | PASS
|  | 9, Update Bill Information. | The bill details are updated successfully, and a confirmation message is displayed. |  | PASS
|  | 10, Transfer Bill In Merchant App | “Bill Transfer request submitted Successfully” message displayed |  | PASS
|  | 11, Merchant Transfer Bill with bill successfully transfered message | transferred successfully |  | PASS
|  | 12, Cancel Bill. | The bill is successfully Cancelled, and ”Bill Cancelled Successfully” Message Displayed |  | PASS | doesn't show from which agent the bill is transfered
|  | 13, Canceled Bill requests (in Merchant App requests tab) | The Cancelled requested bills displayed in the request Cancel tab |  | PASS
TC-05 | Feeds | 1, Verify that the Transaction feed is displayed and waiting for incoming transaction message. | Transaction Feed Screen should be visible |  | Not Available for test
TC-06 | Branches | Verify branches listed | The branches should be visible |  | PASS
|  | 1, Add New Branch. | Add New Branch Pop up Should Display and has to add branch successfully |  | PASS | the app is Adding the same branch with same information
|  | 2, Search Branch By Name | Branches with matching Names should appear in the table. |  | PASS
|  | 3, Update Branch | The Branch Has To Update Successfully |  | PASS
|  | Merge Branch | The Selected Branches Merged Successfully
TC-07 | Settings | 1, Verify Settings displayed. | settings screen will displayed. No error messages displayed. |  | PASS
|  | 2, Update Limit Amount | Settings Updated Successfully Message Displayed |  | PASS |  | Accepted
|  | 3, Update Limit Pending bill | i |  | PASS
|  | 4, Update Distance range | Settings Updated Successfully Message Displayed |  | PASS |  | Accepted

## Sales agent App
|  |  | Project Name | Salse agent App
Project Manager
Tested by
Start date
End date
Test ID | Features | Test Cases | Expected Result | Actual Result | PASS / FAIL | Remarks | Developer Comments
TC-01 | Authentication | 1, Login with valid credentials. | Successfully logged in and redirected to the merchant dashboard. No error messages displayed. |  | Pass | at frist log in the app forces to change password but doesn't kickout the agent to login with the new credintial
|  | 2, Logout from Agent account. | User is logged out and redirected to the login page. |  | Pass
TC_02 | Home Screen | 1, Displays agent details correctly | Agent's name, status, total amonut |  | Pass | naming of account status is un clear for customer
|  | 2, Filters Bills by Pending Status | Only "PENDING" bills With agent name,ID, state, reason & amount+currency type are displayed. "Pending" button count matches list. |  | Pass
|  | 3.Filters Bills by Paid Status | Only "PAID" bills With agent name,ID, reason & amount+currency type are displayed. "Paid" button count matches list |  | Pass
|  | 4, Filters Bills by Cancelled Status | Only "CANCELLED" bills are displayed. "Cancelled" button count matches list. |  | Pass
|  | 5, Filters Bills by Transferred Status | Only "TRANSFER" bills are displayed. "Transfer" button count matches list. |  | Pass
|  | 6, Displays bill details | display Bill amount, status, QR, amount+currency type, order ID, reason, agent ID, State(Transferd:receiver Name&ID/not), and date displayed for each bill match the data in the API response. |  | Not available for Test
|  | 7, Filter bills by date(History Tab) | Bill amount, status, and date displayed for each bill match the data in the API response. |  | Not available for Test
|  | 8, filter paid bills by daily and weekly(History tab) | filter paid bills result by daily and weekly are displayed |  | Not available for Test
|  | 9. Change the Account status | . Change the account status according to the expected result." |  | Pass | the system should have the mechanisim to check if agent has pending bills before merchant deactivate the agent
|  | 9. Change the Account status | . Change the current status according to the expected result." |  | Pass
TC-03 | QR Code Generation | 1, Generates a QR code with a specific amount and description. | A QR code is displayed. The data encoded within the QR code contains the specified amount and description. |  | Not available for Test
|  | 2. save the generated bill | The generated bill with QR is listed at Pending/paid/ bill list |  | Pass
|  | 3.when it paid the status has to change pending to the paid | Status Changed From pending to paid |  | Not available for Test
TC-4 | Payment detail | 1, Displays agent list in transfer bill. | All agents are displayed with a unique user name to select an agent for transfer |  | Pass
|  | 2, Cancel a bill | The bill has been cancelled seccessfully |  | Pass | this filter shows bills that are requested for canclation but not approved by the merchant yet
|  | 2, transfer a bill | the bill has been transferred and status shows transfer |  | Pass | merchant can transfer bill to the owner twice
TC-5 | Word correction | 1,All Word typos | Transferred |  | PASS

## Merchant Backoffice
|  |  | Project Name | Merchant web | Atlas computer Technology Quality Assurance Team
|  |  | Project Manager | Shiferaw Demlew
|  |  | Tested by | Test team
|  |  | Start date | 2025-04-03
|  |  | End date | Last Updated date - 4/10/2015
Test ID | Features | Test Cases | Expected Result | Actual Result | PASS / FAILS | Remarks | Developers Comments
TC-01 | Merchant App / Merchant Web | Activate button clicked | SMS sends activation code only |  | Pass | Only for web
|  | Reset button clicked | SMS sends activation code |  | Pass | the reset button should not be visible for new customer(should be as label/ hidden)
|  | Pin Reset button clicked | SMS sends PIN only |  | Pass | the pin reset button should not be visible for new customer
|  | Link mutiple account | sucessful linkage of more than one account |  | Not available for Test | feature update | New fueture: will be considered on next release
|  | Authomatic Merchant ID generation |  |  | Pass | The merchant ID must have specific pattern (eg. ''MID''+Phonenumber) | Accepted
|  | Register a customer who has not been previously registered to any digital channel or USSD |  |  | Not available for Test | feature update | New feature: will be considered on next release
|  | Block or disable Merchant |  |  | Pass | if the Block is done while the customer is in loggin session ,he can continue using the app as long as he's not loggedout | Accepted
|  | Alter attached account |  |  | Pass | there is no maker and checker concept for updating merchant account | Accepted
TC-11
TC-12
TC-13
TC-14
TC-15
TC-16
TC-17
TC-18
TC-19
TC-20
TC-21
TC-22
TC-23
TC-24
TC-25
TC-26
TC-27
TC-28
TC-29
TC-30
TC-31
TC-32
TC-33
TC-34
TC-35
TC-36
TC-37
TC-38
TC-39
TC-40
TC-41
TC-42
TC-43
TC-44
TC-45
TC-46
TC-47
TC-48
TC-49
TC-50
TC-51
TC-52
TC-53
TC-54
TC-55
TC-56
TC-57
TC-58
TC-59
TC-60
TC-61
TC-62
TC-63
TC-64
TC-65
TC-66
TC-67
TC-68
TC-69
TC-70
TC-71
TC-72
TC-73
TC-74
TC-75
TC-76
TC-77
TC-78
TC-79
TC-80
TC-81
TC-82
TC-83
TC-84
TC-85
TC-86
TC-87
TC-88
TC-89
TC-90
TC-91
TC-92
TC-93
TC-94
TC-95
TC-96
TC-97
TC-98
TC-99
TC-100
TC-101
TC-102
TC-103
TC-104
TC-105
TC-106
TC-107
TC-108
TC-109
TC-110
TC-111
TC-112
TC-113
TC-114
TC-115
TC-116
TC-117
TC-118
TC-119
TC-120
TC-121
TC-122
TC-123
TC-124
TC-125
TC-126
TC-127
TC-128
TC-129
TC-130
TC-131
TC-132
TC-133
TC-134
TC-135
TC-136
TC-137
TC-138
TC-139
TC-140
TC-141
TC-142
TC-143
TC-144
TC-145
TC-146
TC-147
TC-148
TC-149
TC-150
TC-151
TC-152
TC-153
TC-154